## 내보내기 요약
이 문서는 Numbers에서 내보낸 문서입니다. 각 표가 Excel 워크시트로 변환되었습니다. 각 Numbers 시트에 있는 모든 다른 대상체는 개별 워크시트에 위치 지정되었습니다. Excel에서 공식 계산이 다를 수 있으니 유의하십시오.
Numbers 시트 이름 | Numbers 표 이름 | Excel 워크시트 이름
Summary
| Summary | Summary - Summary
WBS
| WBS — Rhymix CMS → Vite React + Firebase Migration | WBS - WBS — Rhymix CMS → Vite R
Tech Stack
| Tech Stack | Tech Stack - Tech Stack
API Cheat Sheet
| API Cheat Sheet | API Cheat Sheet - API Cheat She

## Summary - Summary
Summary
Effort Summary by Phase
Phase | Tasks | Est. Days | Key Deliverable
Phase 0 — Project Setup & Architecture | 19 | 11 | Firebase project, Vite scaffold, CI/CD, API strategy, env vars
Phase 1 — Authentication & Member | 23 | 15 | Firebase Auth, session bridge, profile CRUD, member admin
Phase 2 — Content: Board/Document/Comment | 28 | 24 | Document list/write/delete, files, threaded comments, voting
Phase 3 — Navigation & Site Structure | 8 | 5.5 | Menu API, React Router, breadcrumb, homepage, static pages
Phase 4 — Notifications & Messaging | 11 | 8.5 | ncenterlite bell/list, FCM push, private messages, friends
Phase 5 — Advanced Features | 22 | 14 | Search, tags, polls, points, extra vars, RSS feeds
Phase 6 — Admin Panel | 22 | 17 | Dashboard, board/module admin, moderation, spam filter
Phase 7 — Firebase Functions & Backend | 15 | 11.5 | API proxy, Firestore sync, Storage rules, utility functions
Phase 8 — UI/UX & Polish | 14 | 10 | Design system, SEO, accessibility, i18n, error handling
Phase 9 — Testing & QA | 12 | 8 | Vitest unit tests, Playwright E2E, Lighthouse, security review
Phase 10 — Production Launch | 12 | 6 | Domain, App Check, security rules audit, monitoring, rollback
TOTAL | 186 | 130.5 | Full Rhymix → Vite React + Firebase migration

## WBS - WBS — Rhymix CMS → Vite R
WBS — Rhymix CMS → Vite React + Firebase Migration
WBS ID | Task / Deliverable | Stack / Layer | Owner | Est. Days | Priority | Depends On | Notes
0 | PHASE 0 — Project Setup & Architecture Decisions
0.1 | Environment & Tooling Setup |  | Infra / Dev | 3d | Critical
0.1.1 | Create Firebase project (Blaze plan) | Firebase Console | Infra | 0.5d | Critical | — | Enable Firestore, Auth, Storage, Functions, Hosting
0.1.2 | Scaffold Vite + React + TypeScript project | Frontend | Dev | 0.5d | Critical | — | npm create vite@latest — TypeScript template
0.1.3 | Install core dependencies | Frontend | Dev | 0.5d | Critical | 0.1.2 | react-router-dom v6, firebase v10, axios, TanStack Query, Zustand, react-hook-form, zod, Day.js, DOMPurify
0.1.4 | Configure Firebase SDK (firebaseConfig.ts) | Frontend | Dev | 0.5d | Critical | 0.1.1,0.1.3 | Init app, auth, firestore, storage, functions instances
0.1.5 | Configure Vite environment variables | Frontend | Dev | 0.5d | High | 0.1.2 | VITE_FIREBASE_*, VITE_API_BASE_URL per .env.development / .env.production
0.1.6 | Setup ESLint + Prettier + Husky pre-commit | Frontend | Dev | 0.5d | Medium | 0.1.2 | Enforce code style; block bad commits
0.1.7 | Configure Firebase Hosting (firebase.json) | DevOps | Dev | 0.5d | High | 0.1.1 | SPA rewrite rule; .firebaserc; hosting target
0.2 | Architecture & API Strategy |  | Arch / Lead | 2d | Critical
0.2.1 | Decide Rhymix integration pattern | Architecture | Lead | 1d | Critical | — | Recommended: Option A — Rhymix as pure JSON API backend (fastest); Option B — full Firebase rewrite; Option C — hybrid
0.2.2 | Design axios API client layer | Frontend | Dev | 0.5d | Critical | 0.2.1 | Base URL, CSRF token interceptor, JSON response normaliser, global error handler
0.2.3 | Define TypeScript types for all Rhymix data models | Frontend | Dev | 1d | High | 0.2.1 | Document, Comment, Member, File, Notification, Poll — based on DB schema specs
0.2.4 | Define React Router v6 route map | Frontend | Dev | 0.5d | High | 0.2.1 | Map /login /signup /{mid} /{mid}/{doc_srl} to components; auth guards
0.2.5 | Write Firebase Security Rules skeleton | Firebase | Dev | 0.5d | Critical | 0.1.1 | Deny-all baseline for Firestore + Storage; unlock per feature
0.3 | CI/CD Pipeline |  | DevOps | 2d | High
0.3.1 | GitHub Actions: lint + type-check + build | DevOps | Dev | 0.5d | High | 0.1.2 | On PR: eslint, tsc --noEmit, vite build
0.3.2 | GitHub Actions: deploy to Firebase Hosting (prod) | DevOps | Dev | 0.5d | High | 0.1.7,0.3.1 | On merge to main: firebase deploy --only hosting
0.3.3 | Firebase Hosting preview channels for PRs | DevOps | Dev | 0.5d | Medium | 0.3.2 | Automatic preview URL per PR; comment on PR
0.3.4 | Firebase Functions deploy pipeline | DevOps | Dev | 0.5d | High | 0.3.2 | firebase deploy --only functions; TypeScript compile step
1 | PHASE 1 — Authentication & Member System
1.1 | Firebase Auth + Rhymix Session Bridge |  | Auth | 4d | Critical |  | 0.2.1
1.1.1 | Firebase Auth: email/password signup | Frontend / Firebase | Dev | 1d | Critical | 0.1.4 | createUserWithEmailAndPassword → Cloud Function syncs to Rhymix procMemberInsert
1.1.2 | Firebase Auth: email/password login | Frontend / Firebase | Dev | 1d | Critical | 0.1.4 | signInWithEmailAndPassword → call Rhymix procMemberLogin to issue session cookie
1.1.3 | Firebase Auth: logout | Frontend / Firebase | Dev | 0.5d | Critical | 1.1.2 | signOut() + call procMemberLogout to clear Rhymix session
1.1.4 | Google OAuth login | Frontend / Firebase | Dev | 1d | High | 0.1.4 | GoogleAuthProvider; map Firebase user to Rhymix member via email
1.1.5 | Cloud Function: syncAuthToRhymix | Functions | Dev | 1d | Critical | 0.3.4 | onCreate trigger → POST procMemberInsert; store member_srl in Firestore user_profiles
1.1.6 | Auth state store (Zustand) | Frontend | Dev | 0.5d | Critical | 1.1.2 | currentUser, member_srl, nick_name, is_admin, groups — persisted via onAuthStateChanged
1.1.7 | ProtectedRoute component | Frontend | Dev | 0.5d | Critical | 1.1.6 | Redirect to /login if not authed; optional role guard (is_admin)
1.1.8 | CSRF token fetch and axios interceptor | Frontend | Dev | 0.5d | Critical | 1.1.2 | GET xe.csrf_token from Rhymix HTML meta; inject _rx_csrf_token in all POST requests
1.2 | Member Profile & Account Pages |  | Frontend | 5d | High |  | 1.1
1.2.1 | Login page | Frontend | Dev | 1d | Critical | 1.1.2 | Email + PW form; Google button; link to signup / forgot password
1.2.2 | Signup / Registration page | Frontend | Dev | 1d | Critical | 1.1.1 | Dynamic fields from member join form config; react-hook-form + zod validation
1.2.3 | Find account / reset password page | Frontend | Dev | 0.5d | Medium | 1.1.2 | procMemberFindAccount + procMemberResetPassword flow
1.2.4 | Email verification handler | Frontend | Dev | 0.5d | High | 1.1.1 | Handle procMemberAuthAccount route /auth/{srl}/{key}
1.2.5 | Member profile view page | Frontend | Dev | 1d | High | 1.1.6 | dispMemberInfo — avatar, nick_name, email, point, groups, extra_vars
1.2.6 | Edit profile page | Frontend | Dev | 1d | High | 1.2.5 | procMemberModifyInfo — nick_name, email, extra vars; re-auth check
1.2.7 | Change password page | Frontend | Dev | 0.5d | Medium | 1.2.5 | procMemberModifyInfoBefore (pw recheck) → procMemberModifyPassword
1.2.8 | Profile image upload | Frontend | Dev | 0.5d | Medium | 1.2.5 | procMemberInsertProfileImage (multipart); preview & delete
1.2.9 | My documents / comments / scraps pages | Frontend | Dev | 1d | Medium | 1.2.5 | dispMemberOwnDocument, dispMemberOwnComment, dispMemberScrappedDocument — paginated lists
1.2.10 | Active logins page | Frontend | Dev | 0.5d | Low | 1.2.5 | dispMemberActiveLogins — list sessions; revoke button → procMemberDeleteAutologin
1.3 | Member Admin Panel |  | Frontend / Admin | 3d | Medium |  | 1.2
1.3.1 | Admin: member list (search, filter by group/status) | Frontend / Admin | Dev | 1d | Medium | 1.2.5 | dispMemberAdminList — paginated table
1.3.2 | Admin: member detail + edit + delete | Frontend / Admin | Dev | 1d | Medium | 1.3.1 | dispMemberAdminInfo, procMemberAdminInsert, procMemberAdminDelete
1.3.3 | Admin: group management (CRUD + assign members) | Frontend / Admin | Dev | 1d | Medium | 1.3.1 | dispMemberAdminGroupList; procMemberAdminInsertGroup/UpdateGroup/DeleteGroup
2 | PHASE 2 — Core Content: Board / Document / Comment
2.1 | Document List & View |  | Frontend | 5d | Critical |  | 1.1
2.1.1 | Board list page (dispBoardContent) | Frontend | Dev | 1d | Critical | 0.2.3 | Fetch docs: mid, page, category_srl, search_target/keyword; paginated card/row list
2.1.2 | Document card / row component | Frontend | Dev | 0.5d | Critical | 2.1.1 | Title, nick_name, regdate (parsed), views, votes, comment count, category, notice badge
2.1.3 | Document detail page | Frontend | Dev | 1.5d | Critical | 2.1.1 | Render HTML content via DOMPurify; author/date/vote meta; attachments; edit/delete for owner
2.1.4 | Date parse utility (YYYYMMDDHHIISS) | Frontend | Dev | 0.5d | Critical | 0.2.3 | Parse Rhymix internal date; Day.js relative time display
2.1.5 | Category sidebar / filter | Frontend | Dev | 0.5d | High | 2.1.1 | getDocumentCategories → tree render; click to filter list with category_srl
2.1.6 | Search bar component | Frontend | Dev | 0.5d | High | 2.1.1 | search_target dropdown + keyword input; debounced refetch
2.1.7 | Pagination component (reusable) | Frontend | Dev | 0.5d | High | 2.1.1 | Props: total_page, cur_page; prev/next/numbered links
2.1.8 | Notice / pinned document display | Frontend | Dev | 0.5d | Medium | 2.1.1 | Separate notice list at top; is_notice Y/A flags
2.2 | Document Write / Edit / Delete |  | Frontend | 5d | Critical |  | 2.1
2.2.1 | Write / edit form page | Frontend | Dev | 1.5d | Critical | 1.1.7 | react-hook-form; title, content, category_srl, tags, is_notice toggle; procBoardInsertDocument
2.2.2 | Rich text editor (TipTap) | Frontend | Dev | 2d | Critical | 2.2.1 | TipTap v2; toolbar; image paste → procFileUpload; HTML output sanitised by server HTMLFilter
2.2.3 | Extra vars (custom fields) in write form | Frontend | Dev | 1d | High | 2.2.1 | Fetch board extra var definitions; render text/select/checkbox/file inputs per field type
2.2.4 | Delete document flow | Frontend | Dev | 0.5d | High | 2.2.1 | Confirm modal → procBoardDeleteDocument → redirect to list
2.2.5 | Secret / password-protected document | Frontend | Dev | 0.5d | Medium | 2.2.1 | is_secret flag + password field; procBoardVerificationPassword for read access
2.2.6 | Auto-save draft (procEditorSaveDoc) | Frontend | Dev | 1d | Medium | 2.2.1 | POST every 30s; restore offer on reopen; procEditorRemoveSavedDoc after publish
2.3 | File Attachments |  | Frontend | 3d | High |  | 2.2
2.3.1 | File upload component | Frontend | Dev | 1d | High | 1.1.8 | Drag-and-drop + click; procFileUpload (multipart, no CSRF); progress bar; file list with remove
2.3.2 | Attach files to document on submit | Frontend | Dev | 0.5d | Critical | 2.3.1 | Pass editor_sequence; server links files to document_srl on procBoardInsertDocument
2.3.3 | File list display in document view | Frontend | Dev | 0.5d | High | 2.1.3 | filename, size, download_count; link to procFileDownload
2.3.4 | Inline image preview | Frontend | Dev | 0.5d | Medium | 2.1.3 | Images use uploaded_filename path + RX_BASEURL; video thumbnails
2.3.5 | Chunked upload for large files | Frontend | Dev | 1d | Medium | 2.3.1 | Slice File object; Content-Range header per chunk; sequential POSTs
2.4 | Comments |  | Frontend | 4.5d | Critical |  | 2.1
2.4.1 | Threaded comment list | Frontend | Dev | 1.5d | Critical | 2.1.3 | Recursive render using head/arrange/depth; indent replies; load-more pagination
2.4.2 | Comment write form | Frontend | Dev | 1d | Critical | 2.4.1 | procBoardInsertComment; parent_srl for replies; guest name+pw; optional file upload
2.4.3 | Comment edit / delete | Frontend | Dev | 0.5d | High | 2.4.1 | Show actions for own comments; procBoardDeleteComment
2.4.4 | Comment vote (up/down) | Frontend | Dev | 0.5d | High | 2.4.1 | procCommentVoteUp/Down; optimistic count update
2.4.5 | Secret comment handling | Frontend | Dev | 0.5d | Medium | 2.4.1 | Placeholder for is_secret='Y'; password prompt via procBoardVerificationPassword
2.4.6 | Comment abuse report | Frontend | Dev | 0.5d | Low | 2.4.1 | dispCommentDeclare / procCommentDeclare; member only
2.5 | Voting & Reactions |  | Frontend | 2d | High |  | 2.1
2.5.1 | Document vote buttons (up/down) | Frontend | Dev | 0.5d | High | 2.1.3 | procDocumentVoteUp/Down; optimistic voted_count update
2.5.2 | Vote cancel | Frontend | Dev | 0.5d | Medium | 2.5.1 | procDocumentVoteUpCancel/DownCancel; toggle state
2.5.3 | Voters list popup | Frontend | Dev | 0.5d | Low | 2.5.1 | dispBoardVoteLog → member names; requires vote_log_view grant
2.5.4 | Document abuse report | Frontend | Dev | 0.5d | Medium | 2.1.3 | dispDocumentDeclare / procDocumentDeclare; member only; confirm modal
3 | PHASE 3 — Navigation & Site Structure
3.1 | Navigation & Routing |  | Frontend | 3.5d | Critical |  | 0.2.4
3.1.1 | Cloud Function: getMenuData | Functions | Dev | 1d | Critical | 0.3.4 | Query Rhymix menu_item table; return JSON tree; cache in Firestore 5 min
3.1.2 | Top nav bar component | Frontend | Dev | 1d | Critical | 3.1.1 | Render menu tree; active state; mobile hamburger; auth-aware login/profile links
3.1.3 | Dynamic route generation from menu items | Frontend | Dev | 0.5d | High | 3.1.1 | Map mid → component; React Router v6 <Route> per menu item
3.1.4 | Sidebar navigation (per-board context) | Frontend | Dev | 0.5d | High | 3.1.1 | Optional collapsible sidebar with category tree
3.1.5 | Breadcrumb component | Frontend | Dev | 0.5d | Low | 3.1.3 | Reflect board/category/document path
3.1.6 | 404 Not Found page | Frontend | Dev | 0.5d | Medium | 3.1.3 | Catch-all route; friendly message + link home
3.2 | Homepage & Static Pages |  | Frontend | 2d | High |  | 3.1
3.2.1 | Homepage component | Frontend | Dev | 1d | High | 3.1.3 | Render Rhymix default module (page or board); featured documents
3.2.2 | Page module renderer | Frontend | Dev | 1d | High | 3.2.1 | Fetch Rhymix page HTML; render via dangerouslySetInnerHTML; DOMPurify sanitise
4 | PHASE 4 — Notifications, Messaging & Social
4.1 | Notification Center (ncenterlite) |  | Frontend | 4.5d | High |  | 1.1
4.1.1 | Cloud Function: getNotificationCount | Functions | Dev | 0.5d | High | 0.3.4 | Lightweight unread count; cache 30s per user
4.1.2 | Notification bell icon with unread badge | Frontend | Dev | 0.5d | High | 4.1.1 | Poll count every 30s; or use Firestore real-time listener
4.1.3 | Notification dropdown / panel | Frontend | Dev | 1d | High | 4.1.2 | Recent 10 notifications; mark-all-read → procNcenterliteNotifyReadAll
4.1.4 | Full notification list page (paginated) | Frontend | Dev | 1d | High | 4.1.3 | dispNcenterliteNotifyList; grouped by type; click → procNcenterliteRedirect
4.1.5 | Notification preferences page | Frontend | Dev | 0.5d | Medium | 4.1.4 | dispNcenterliteUserConfig; toggle per notify_type
4.1.6 | FCM push notification setup | Frontend / Firebase | Dev | 1d | Medium | 4.1.2 | Request permission; getToken(); procMemberRegisterDevice; Cloud Function dispatches FCM
4.2 | Private Messaging |  | Frontend | 4d | High |  | 1.1
4.2.1 | Message inbox (received / sent / stored tabs) | Frontend | Dev | 1d | High | 1.1.6 | dispCommunicationMessages; paginated
4.2.2 | Message detail view | Frontend | Dev | 0.5d | High | 4.2.1 | Render HTML body; reply / delete actions
4.2.3 | Compose message modal / page | Frontend | Dev | 1d | High | 4.2.1 | procCommunicationSendMessage; recipient search by nick_name; check allow_message flag
4.2.4 | New message indicator in navbar | Frontend | Dev | 0.5d | High | 4.2.1 | getNewMessageCount poll or FCM push
4.2.5 | Friend list & management | Frontend | Dev | 1d | Medium | 4.2.1 | dispCommunicationFriend; add/remove/group friends
5 | PHASE 5 — Advanced Features
5.1 | Search |  | Frontend / Functions | 3d | High |  | 2.1
5.1.1 | Cloud Function: searchDocuments proxy | Functions | Dev | 0.5d | High | 0.3.4 | Proxy to IS action on Rhymix; normalise result JSON
5.1.2 | Global search page | Frontend | Dev | 1d | High | 5.1.1 | search_target dropdown + keyword; results grouped by module type
5.1.3 | Search result item component | Frontend | Dev | 1d | High | 5.1.2 | Highlight matched keyword in title/excerpt; show source module badge
5.1.4 | Search autocomplete / suggestions | Frontend | Dev | 0.5d | Low | 5.1.2 | Debounced API call; dropdown suggestions
5.2 | Tags |  | Frontend | 2d | Medium |  | 2.2
5.2.1 | Tag input in write form | Frontend | Dev | 1d | Medium | 2.2.1 | Comma-separated tag chips; autocomplete from getTagList; max count config
5.2.2 | Tag cloud widget | Frontend | Dev | 0.5d | Medium | 2.1.1 | TagModel::getTagList → weighted chip cloud
5.2.3 | Tag-filtered document list | Frontend | Dev | 0.5d | Medium | 5.2.1 | search_target=tag&search_keyword={tag} parameter
5.3 | Polls |  | Frontend | 3d | Medium |  | 2.1
5.3.1 | Poll display component | Frontend | Dev | 1d | Medium | 2.1.3 | getPollstatus → option list; voted state; result bars
5.3.2 | Poll voting action | Frontend | Dev | 0.5d | Medium | 5.3.1 | procPoll; single/multi-select; no-revote guard
5.3.3 | Poll results visualisation | Frontend | Dev | 0.5d | Medium | 5.3.1 | Percentage bars or recharts pie; vote count per item
5.3.4 | Poll creation in write form | Frontend | Dev | 1d | Low | 2.2.1 | procPollInsert; attach poll_srl to document
5.4 | Points / Gamification Display |  | Frontend | 2d | Low |  | 1.2
5.4.1 | Member point display | Frontend | Dev | 0.5d | Low | 1.2.5 | getMembersPointInfo → show in profile & user cards
5.4.2 | Level / group badge | Frontend | Dev | 0.5d | Low | 5.4.1 | Current group name/icon based on point tier
5.4.3 | Point history page | Frontend | Dev | 1d | Low | 5.4.1 | If point log endpoint available; earn/spend history list
5.5 | Extra Vars (Custom Fields) |  | Frontend | 3d | Medium |  | 2.2
5.5.1 | Fetch extravar field definitions | Frontend | Dev | 0.5d | Medium | 0.2.3 | API call per module_srl; cache definitions
5.5.2 | Dynamic extra var form renderer | Frontend | Dev | 1.5d | Medium | 5.5.1 | text/select/checkbox/file/datetime/tel inputs per field type; zod validation schema
5.5.3 | Display extra var values in document/profile | Frontend | Dev | 1d | Medium | 5.5.2 | Read extra_vars object from JSON; render label + value pairs
5.6 | RSS Feeds |  | Frontend | 1d | Low |  | 2.1
5.6.1 | RSS/Atom link discovery in <head> | Frontend | Dev | 0.5d | Low | 2.1.1 | react-helmet-async <link rel='alternate'> per board mid
5.6.2 | Feed links in board UI | Frontend | Dev | 0.5d | Low | 2.1.1 | RSS icon → ?act=rss; Atom icon → ?act=atom
6 | PHASE 6 — Admin Panel
6.1 | Admin Shell & System Config |  | Frontend / Admin | 5d | High |  | 1.1
6.1.1 | Admin route guard (root only) | Frontend / Admin | Dev | 0.5d | Critical | 1.1.7 | Check is_admin='Y'; redirect to home if not admin
6.1.2 | Admin layout (sidebar + content area) | Frontend / Admin | Dev | 1d | High | 6.1.1 | Separate shell from public layout; collapsible nav; admin breadcrumb
6.1.3 | Dashboard page | Frontend / Admin | Dev | 1d | High | 6.1.2 | dispAdminIndex → member count, doc count, comment count, recent activity
6.1.4 | System settings form tabs | Frontend / Admin | Dev | 1.5d | High | 6.1.2 | General / SEO / Security / Advanced / Debug → procAdminUpdate* actions
6.1.5 | Site lock / maintenance mode toggle | Frontend / Admin | Dev | 0.5d | High | 6.1.4 | procAdminUpdateSitelock; maintenance banner on public site
6.1.6 | Cache clear button | Frontend / Admin | Dev | 0.5d | Medium | 6.1.2 | procAdminRecompileCacheFile; confirm dialog; success toast
6.2 | Module & Board Administration |  | Frontend / Admin | 5d | High |  | 6.1
6.2.1 | Module instance list | Frontend / Admin | Dev | 1d | High | 6.1.2 | getModuleAdminModuleList → all mid/module/domain entries
6.2.2 | Board create / edit form | Frontend / Admin | Dev | 1.5d | High | 6.2.1 | procBoardAdminInsertBoard/UpdateBoard — list_count, grants, skin, categories
6.2.3 | Board category management | Frontend / Admin | Dev | 1d | High | 6.2.2 | procDocumentInsertCategory/DeleteCategory/MoveCategory — tree editor
6.2.4 | Module permission (grant) setup | Frontend / Admin | Dev | 1d | Medium | 6.2.1 | procModuleAdminModuleGrantSetup — group-level access per grant type
6.2.5 | Menu editor | Frontend / Admin | Dev | 1.5d | High | 6.1.2 | dispMenuAdminSiteMap — drag-and-drop tree; add/edit/delete; procMenuAdminMakeXmlFile
6.3 | Content Moderation |  | Frontend / Admin | 4d | High |  | 6.1
6.3.1 | Document admin list + bulk actions | Frontend / Admin | Dev | 1d | High | 6.1.2 | dispDocumentAdminList — filter, select, bulk delete/move/status
6.3.2 | Comment admin list + bulk actions | Frontend / Admin | Dev | 1d | High | 6.1.2 | dispCommentAdminList — filter, select, bulk delete/status
6.3.3 | Declared (reported) content management | Frontend / Admin | Dev | 1d | Medium | 6.3.1 | dispDocumentAdminDeclared + dispCommentAdminDeclared; cancel/delete
6.3.4 | Spam filter admin (IP / word / CAPTCHA) | Frontend / Admin | Dev | 1d | Medium | 6.1.2 | IP blacklist + word blacklist CRUD; reCAPTCHA/Turnstile config toggle
6.4 | File & Layout Admin |  | Frontend / Admin | 3d | Medium |  | 6.1
6.4.1 | File manager list | Frontend / Admin | Dev | 1d | Medium | 6.1.2 | dispFileAdminList — file table; download count; bulk delete
6.4.2 | File upload config | Frontend / Admin | Dev | 0.5d | Medium | 6.4.1 | procFileAdminInsertUploadConfig — max size, allowed extensions per module
6.4.3 | Layout instance list & skin assignment | Frontend / Admin | Dev | 1.5d | Medium | 6.1.2 | dispLayoutAdminInstalledList; assign layout to modules
7 | PHASE 7 — Firebase Backend (Cloud Functions)
7.1 | API Proxy & Utility Functions |  | Functions | 5d | High |  | 0.3.4
7.1.1 | Functions project structure (TypeScript) | Functions | Dev | 0.5d | Critical | 0.3.4 | src/index.ts; shared http client to Rhymix; env vars RHYMIX_BASE_URL, RHYMIX_ADMIN_PW
7.1.2 | CORS proxy for Rhymix JSON API | Functions | Dev | 1d | Critical | 7.1.1 | Forward React SPA calls to Rhymix; preserve session cookies; inject CSRF token
7.1.3 | Function: getMenuData (cached) | Functions | Dev | 0.5d | Critical | 7.1.1 | Query menu_item → JSON tree; Firestore cache TTL 5 min
7.1.4 | Function: getNotificationCount | Functions | Dev | 0.5d | High | 7.1.1 | Lightweight per-user unread count endpoint
7.1.5 | Function: sendPushNotification | Functions | Dev | 1d | Medium | 7.1.1 | Triggered via ncenterlite webhook or Rhymix trigger → FCM message via firebase-admin
7.1.6 | Function: searchDocuments | Functions | Dev | 0.5d | High | 7.1.1 | Proxy to IS action; return normalised result JSON
7.1.7 | Function: getTagCloud | Functions | Dev | 0.5d | Low | 7.1.1 | Query tags table; cache result in Firestore
7.1.8 | Function: getRssFeed | Functions | Dev | 0.5d | Low | 7.1.1 | Proxy ?act=rss; return XML with correct Content-Type
7.2 | Firestore Data Sync |  | Functions | 4d | Medium |  | 7.1
7.2.1 | Sync member profile to Firestore on login | Functions | Dev | 1d | High | 7.1.2 | Auth onCreate/onLogin → mirror member_srl, nick_name, profile_image, groups, is_admin
7.2.2 | Firestore collection: user_profiles schema | Firebase | Dev | 0.5d | High | 7.2.1 | {uid, member_srl, nick_name, profile_image, groups[], point, is_admin, updated_at}
7.2.3 | Firestore collection: notifications (mirror) | Functions | Dev | 1d | Medium | 7.2.1 | Write ncenterlite records → Firestore for real-time listener in React
7.2.4 | Firebase Security Rules (Firestore + Storage) | Firebase | Dev | 1.5d | Critical | 7.2.1 | User can read/write own profile; read-only others; notifications self-only; admin full
7.3 | Firebase Storage Strategy |  | Firebase | 2.5d | Medium |  | 2.3
7.3.1 | Decide file storage strategy | Architecture | Lead | 0.5d | High | 0.2.1 | Option A (recommended): keep files in Rhymix files/attach/; Option B: mirror to Firebase Storage
7.3.2 | Firebase Storage security rules | Firebase | Dev | 1d | High | 7.3.1 | Auth required for upload; public read for images; file size limit; allowed MIME types
7.3.3 | Profile image via Firebase Storage (optional) | Frontend / Firebase | Dev | 1d | Medium | 7.3.2 | Upload to Storage → signed URL → save to Firestore + procMemberInsertProfileImage
8 | PHASE 8 — UI/UX, Design System & Polish
8.1 | Design System |  | Frontend | 5d | High |  | 0.1
8.1.1 | Tailwind CSS setup + design tokens | Frontend | Dev | 0.5d | High | 0.1.2 | tailwind.config.ts; colors, spacing, typography; dark mode class strategy
8.1.2 | Base component library | Frontend | Dev | 2d | High | 8.1.1 | Button, Input, Select, Checkbox, Modal, Toast, Spinner, Badge, Avatar, Card, Dropdown
8.1.3 | Responsive layout grid | Frontend | Dev | 0.5d | High | 8.1.1 | 12-col grid; breakpoints sm/md/lg/xl; board list adapts to screen
8.1.4 | Loading states & skeleton screens | Frontend | Dev | 1d | Medium | 8.1.2 | TanStack Query suspense + skeleton for list, detail, comments
8.1.5 | Error boundary + global error toast | Frontend | Dev | 1d | High | 8.1.2 | React ErrorBoundary; axios response error → toast with message field
8.2 | SEO & Meta |  | Frontend | 2d | High |  | 2.1
8.2.1 | react-helmet-async setup | Frontend | Dev | 0.5d | High | 2.1.3 | Per-page title, description, canonical URL, og:* tags
8.2.2 | OpenGraph tags for document pages | Frontend | Dev | 0.5d | High | 8.2.1 | og:title, og:description (content excerpt), og:image (cover file or site default)
8.2.3 | JSON-LD structured data | Frontend | Dev | 0.5d | Medium | 8.2.1 | Article schema for document; BreadcrumbList for board navigation
8.2.4 | Sitemap generation (Cloud Function) | Functions | Dev | 0.5d | Low | 7.1.1 | Generate sitemap.xml from module list + recent docs; ping Google
8.3 | Accessibility & i18n |  | Frontend | 3d | Medium |  | 8.1
8.3.1 | ARIA labels on all interactive elements | Frontend | Dev | 1d | Medium | 8.1.2 | Buttons, forms, modals, nav — WCAG 2.1 AA target
8.3.2 | Keyboard navigation & focus management | Frontend | Dev | 0.5d | Medium | 8.3.1 | Focus trap in modals; skip-to-content link; visible focus ring
8.3.3 | i18n setup (react-i18next) | Frontend | Dev | 1d | Medium | 0.1.3 | Extract Rhymix lang strings to JSON; ko/en namespace minimum; lazy load
8.3.4 | Language switcher UI | Frontend | Dev | 0.5d | Medium | 8.3.3 | Dropdown in header; set lang_type cookie; refetch content with new lang
9 | PHASE 9 — Testing & QA
9.1 | Unit & Component Testing |  | QA | 4d | High |  | 2.1
9.1.1 | Vitest + React Testing Library setup | QA | Dev | 0.5d | High | 0.1.2 | vitest.config.ts; jsdom; coverage threshold ≥70% on critical paths
9.1.2 | Unit tests: API client & date utilities | QA | Dev | 1d | High | 0.2.2 | CSRF interceptor, date parser, response normaliser, error handler
9.1.3 | Component tests: auth flows | QA | Dev | 1d | High | 1.1 | Login form validation; signup flow; ProtectedRoute redirect
9.1.4 | Component tests: document list + detail | QA | Dev | 1d | High | 2.1 | Render list; pagination click; search submit; vote button state
9.1.5 | Component tests: comment thread | QA | Dev | 0.5d | Medium | 2.4 | Nested render; reply form submit; vote toggle
9.2 | Integration & E2E Testing |  | QA | 4d | High |  | 6.1
9.2.1 | Playwright E2E setup | QA | Dev | 1d | High | 0.3.1 | playwright.config.ts; test against Firebase preview channel
9.2.2 | E2E: login → write document → comment flow | QA | Dev | 1d | Critical | 9.2.1 | Full happy path: auth, board write, comment, verify
9.2.3 | E2E: file upload flow | QA | Dev | 0.5d | High | 9.2.1 | Upload, attach to document, download verify
9.2.4 | E2E: admin create board + moderate | QA | Dev | 0.5d | High | 9.2.1 | Admin login, board create, document create, delete flow
9.2.5 | Lighthouse CI (performance + a11y) | QA | Dev | 0.5d | Medium | 9.2.1 | LCP<2.5s, CLS<0.1, FID<100ms; a11y score ≥90
9.2.6 | Security review | QA | Lead | 1d | Critical | 9.2.1 | XSS: DOMPurify on all HTML; CSRF: token flow; auth: protected routes; Firebase rules: deny defaults
9.2.7 | Cross-browser & responsive QA | QA | Dev | 0.5d | High | 9.2.1 | Chrome/Firefox/Safari; mobile 375px; tablet 768px
10 | PHASE 10 — Production Launch
10.1 | Pre-Launch Checklist |  | DevOps / Lead | 3.5d | Critical |  | 9.2
10.1.1 | Custom domain on Firebase Hosting | DevOps | Dev | 0.5d | Critical | 0.3.2 | DNS A/CNAME; SSL auto-provisioned by Firebase
10.1.2 | Production Firebase environment variables | DevOps | Dev | 0.5d | Critical | 0.1.5 | VITE_FIREBASE_* for prod project; separate prod/staging Firebase projects
10.1.3 | Rhymix CORS + CSRF config for prod domain | DevOps | Dev | 0.5d | Critical | 0.2.2 | security.csrf_allow_origins includes Firebase Hosting domain
10.1.4 | Firebase App Check (reCAPTCHA Enterprise) | Firebase | Dev | 0.5d | High | 0.1.4 | API abuse prevention; enforce in Functions
10.1.5 | Final Firebase Security Rules audit | Firebase | Dev | 1d | Critical | 7.2.4 | No unintended public write; test with Firebase emulator
10.1.6 | CDN + cache headers on Firebase Hosting | DevOps | Dev | 0.5d | High | 0.3.2 | Static assets: 1y cache; HTML: no-cache; API responses: no-store
10.1.7 | Error monitoring (Sentry) | DevOps | Dev | 0.5d | High | 0.3.2 | Source map upload; alert on error rate spike; performance tracing
10.2 | Launch & Post-Launch |  | Lead | 2.5d | Critical |  | 10.1
10.2.1 | Smoke test production deployment | QA / Lead | Lead | 0.5d | Critical | 10.1 | Login, read, write, file upload, admin — all critical flows
10.2.2 | Firebase quota + billing monitoring | DevOps | Lead | 0.5d | High | 10.2.1 | Functions invocations, Firestore reads/writes, Storage bandwidth alerts
10.2.3 | Performance monitoring (Firebase Perf Mon) | DevOps | Lead | 0.5d | High | 10.2.1 | Real-user metrics; API latency traces; render time
10.2.4 | Rollback plan documentation | Lead | Lead | 0.5d | High | 10.2.1 | Steps to revert to Rhymix HTML rendering if React deployment critical issues
10.2.5 | Knowledge transfer & documentation | Lead | Lead | 1d | Medium | 10.2.1 | README; API endpoint map; Firebase project access; deployment runbook

## Tech Stack - Tech Stack
Tech Stack
Technology Stack Reference
Category | Package / Service | Version | Purpose
Frontend — Core | Vite | ^5.x | Build tool & dev server
| React | ^18.x | UI framework
| TypeScript | ^5.x | Type safety across codebase
| react-router-dom | ^6.x | Client-side routing; data loaders
State Management | Zustand | ^4.x | Auth state, UI globals
| TanStack Query | ^5.x | Server state, caching, pagination, refetch
Forms & Validation | React Hook Form | ^7.x | Form state management
| Zod | ^3.x | Runtime schema validation
Styling | Tailwind CSS | ^3.x | Utility-first styling
| Headless UI / Radix UI | latest | Accessible unstyled UI primitives
| Lucide React | latest | Icon set
Content Safety | DOMPurify | ^3.x | Sanitise Rhymix HTML before dangerouslySetInnerHTML
Date Handling | Day.js | ^1.x | Parse YYYYMMDDHHIISS; relative time; locale
Editor | TipTap | ^2.x | Rich text editor (replaces CKEditor 4)
SEO | react-helmet-async | ^2.x | Per-page title, meta, og:* tags
Charts | recharts | ^2.x | Poll results, admin stats
HTTP Client | axios | ^1.x | Rhymix API calls; CSRF interceptor
Firebase — Client | firebase | ^10.x | Auth, Firestore, Storage, Functions, FCM SDK
Firebase — Server | firebase-admin | ^12.x | Cloud Functions: Firestore, FCM, Auth admin
Firebase — Deploy | firebase-tools | ^13.x | CLI for Hosting + Functions deploy
Functions Runtime | Node.js | 20 LTS | Cloud Functions runtime
| Express | ^4.x | HTTP routing within Functions (optional)
Testing | Vitest | ^2.x | Unit + component test runner
| React Testing Library | ^16.x | Component testing utilities
| Playwright | ^1.x | E2E browser automation
| @axe-core/react | ^4.x | Accessibility auditing in development
Monitoring | Sentry | ^8.x | Error tracking + performance tracing
| Firebase Performance | built-in | Real-user performance monitoring
| Lighthouse CI | latest | Automated performance + a11y scores in CI

## API Cheat Sheet - API Cheat She
API Cheat Sheet
Rhymix API Quick Reference — Key Actions for React Frontend
Module | Action | Method | Permission | Notes / React Usage
── AUTH ──
member | getLoginStatus | POST | guest | No CSRF required; returns {is_logged, member_srl, nick_name, is_admin}
member | procMemberLogin | POST | guest | Fields: user_id, password; sets session cookie
member | procMemberLogout | POST | member | Clears session; call after Firebase signOut()
member | procMemberInsert | POST | guest | Registration; dynamic fields per join form config
member | procMemberAuthAccount | GET | guest | Email verification: /auth/{member_srl}/{auth_key}
member | procMemberResetPassword | POST | guest | Password reset with token from email
member | procMemberRegisterDevice | POST | guest | FCM device token registration for push
── MEMBER ──
member | procMemberModifyInfo | POST | member | Update nick_name, extra vars
member | procMemberModifyPassword | POST | member | Requires procMemberModifyInfoBefore first
member | procMemberInsertProfileImage | POST | member | Multipart; field: image_file
member | getMemberMenu | GET | any | Returns member context menu items
── BOARD / DOCUMENT ──
board | dispBoardContent | GET | list | ?mid=X&page=N&category_srl=Y&search_target=Z&search_keyword=W
board | procBoardInsertDocument | POST | write_document | Fields: mid, title, content, category_srl, tags, is_notice, uploaded_files[]
board | procBoardDeleteDocument | POST | write_document | Field: document_srl
document | procDocumentVoteUp | POST | any | Field: document_srl; returns updated voted_count
document | procDocumentVoteUpCancel | POST | any | Field: document_srl
document | procDocumentTempSave | POST | member | Fields: title, content, editor_sequence
── COMMENT ──
board | procBoardInsertComment | POST | write_comment | Fields: document_srl, content, parent_srl (reply), password (secret)
board | procBoardDeleteComment | POST | write_comment | Field: comment_srl
comment | procCommentVoteUp | POST | any | Field: comment_srl
── FILE ──
file | procFileUpload | POST | any | Multipart; NO CSRF; field: editor_sequence; returns file_srl, uploaded_filename
file | procFileDownload | GET | view | ?file_srl=N; streams file; enforces module access check
file | procFileDelete | POST | any | Field: file_srl; deletes pending upload
── NOTIFICATIONS ──
ncenterlite | procNcenterliteNotifyReadAll | POST | member | Mark all notifications read
ncenterlite | procNcenterliteRedirect | GET | member | ?srl=N; marks read + redirects to content
ncenterlite | procNcenterliteUserConfig | POST | member | Save notification type preferences
── MESSAGING ──
communication | procCommunicationSendMessage | POST | member | Fields: receiver_srl, title, content
communication | procCommunicationDeleteMessage | POST | member | Field: message_srl
── SEARCH ──
integration_search | IS | GET | any | ?mid=X&act=IS&search_target=title_content&search_keyword=Y
── POLL ──
poll | procPoll | POST | any | Fields: poll_srl, item_srl (answer)
poll | getPollstatus | GET | any | ?poll_srl=N; returns options + voted state
── ADMIN ──
admin | procAdminRecompileCacheFile | POST | root | Clear all compiled templates/CSS/JS cache
module | procModuleClearCache | POST | any | Lightweight cache clear; no CSRF required